## Sheet1
A	B	C	D	E	F	G	H	I	J	K	L	M	N	O	P	Q	R	S	T
2
3
4	MPS	0	1	2	3	4	5	6	7	8	9	10
5	MPS: X	10		40			300	200				100
6
7
8	ITEM: X									LEAD TIME:		1
9										LOT SIZE:		1
10		PAST								SAFETY STK:		10
11		DUE	1	2	3	4	5	6	7	8	9	10
12	Gross Requirements	10	0	40	0	0	300	200	0	0	0	100
13	Beginning Inv	60	50	70	30	30	30	10	10	10	10	10
14	Scheduled Receipts		20
15	End Inv (with no P.Rct)	50	70	30	30	30	-270	-190	10	10	10	-90
16	Net Requirements	0	0	0	0	0	280	200	0	0	0	100
17	Planned Receipts	0	0	0	0	0	280	200	0	0	0	100
18	Planned Release	0	0	0	0	280	200	0	0	0	100	0
19
20	Components			Gross Requirements for Components										Qty/EI
21	A	0	0	0	0	280	200	0	0	0	100	0		1
22	B	0	0	0	0	560	400	0	0	0	200	0		2
23	C	0	0	0	0	840	600	0	0	0	300	0		3
24
25
26
27	ITEM: A									LEAD TIME:		3
28										LOT SIZE:		40
29		PAST								SAFETY STK:		20
30		DUE	1	2	3	4	5	6	7	8	9	10
31	Gross Requirements	0	0	0	0	280	200	0	0	0	100	0
32	Beginning Inv	20	20	20	60	60	20	20	20	20	20	40
33	Scheduled Receipts			40
34	End Inv (with no P.Rct)	20	20	60	60	-220	-180	20	20	20	-80	40
35	Net Requirements	0	0	0	0	240	200	0	0	0	100	0
36	Planned Receipts	0	0	0	0	240	200	0	0	0	120	0
37	Planned Release	0	240	200	0	0	0	120	0	0	0	0
38
39	Components			Gross Requirements for Components										Qty/EI
40	None	0	0	0	0	0	0	0	0
41
42
43
44	ITEM: B									LEAD TIME:		3
45										LOT SIZE:		40
46		PAST								SAFETY STK:		20
47		DUE	1	2	3	4	5	6	7	8	9	10
48	Gross Requirements	0	0	0	0	560	400	0	0	0	200	0
49	Beginning Inv	20	20	20	60	60	20	20	20	20	20	20
50	Scheduled Receipts			40
51	End Inv (with no P.Rct)	20	20	60	60	-500	-380	20	20	20	-180	20
52	Net Requirements	0	0	0	0	520	400	0	0	0	200	0
53	Planned Receipts	0	0	0	0	520	400	0	0	0	200	0
54	Planned Release	0	520	400	0	0	0	200	0	0	0	0
55
56	Components			Gross Requirements for Components										Qty/EI
57	C	0	520	400	0	0	0	200	0	0	0	0		1
58
59
60	Gross Reqts for C	0	1	2	3	4	5	6	7	8	9	10
61	Parent: X	0	0	0	0	840	600	0	0	0	300	0
62	Parent: B	0	520	400	0	0	0	200	0	0	0	0
63	Total Reqts for C	0	520	400	0	840	600	200	0	0	300	0
64
65	ITEM: C									LEAD TIME:		3
66										LOT SIZE:		100
67		PAST								SAFETY STK:		10
68		DUE	1	2	3	4	5	6	7	8	9	10
69	Gross Requirements	0	520	400	0	840	600	200	0	0	300	0
70	Beginning Inv	20	20	100	100	100	60	60	60	60	60	60
71	Scheduled Receipts			300
72	End Inv (with no P.Rct)	20	-500	0	100	-740	-540	-140	60	60	-240	60
73	Net Requirements	0	510	10	0	750	550	150	0	0	250	0
74	Planned Receipts	0	600	100	0	800	600	200	0	0	300	0
75	Planned Release	700	800	600	200	0	0	300	0	0	0	0
76
77	Components			Gross Requirements for Components										Qty/EI
78	None	0	0	0	0	0	0	0	0
X
A(1)
C(3)
B(2)
C(1)

NOTE: The PAST DUE column summarizes all activities that should have occured in a previous periods, but did not. The calculations assume this activities will still be completed.
This spreadsheet has no "look ahead" logic. That is, it plans a new receipt whenever the projected ending inventory falls below the safety stock. It does not check for scheduled receipts in later periods that could be used to fill the order. That responsibility is left to the material scheduler.
X
A(1)
C(3)
B(2)
C(1)